## HOME PAGE
CHANGE MANAGEMENT BLUEPRINT
for the adoption of modern technologies
The Blueprint is a tool that assists and guides change leaders throughout the implementation of any technology-related change initiative after the 'Business Case' for the new technology was completed and the decision was made to implement the specific technology.
It can be used either as a full change management process/toolkit or to supplement an existing change management process/toolkit.
Below is a summary of the 3PRS Blueprint's key stages and what you will do during each stage.
WHAT TO KNOW BEFORE YOU START USING THE CHANGE MANAGEMENT BLUEPRINT:
* | Change Management deals with the people side of change, and the main goal is to effectively guide people to transition from a past/present state to a future desired state. It’s the role of management to influence people’s behaviour in reaction to technical/technological changes.
* | The success of your change initiative will be influenced by the availability of critical success factors as input into the preparation and planning phases such as having the organisation's digitisation strategy/journey available, and an understanding of the resources currently available for the new project.
* | As the change leader, you should evaluate not just which steps/templates of the Blueprint to use for your specific change management process, but also how to use the templates to gather the necessary information to facilitate people through the change process.
* | Ultimately, the quality of the information added to the templates will determine the success of the change management process. If any step or specific sub-section of a step is not completed, it should be after due consideration on the impact this might have on the overall success of the project.
HOW TO USE THIS TOOL:
* | The Blueprint is a Microsoft Excel Tool with different worksheets that guide you through completing each step within the 5-Phase Change Management Process. You should start on top of each worksheet and complete all the required templates before progressing to the next worksheet, starting with '1. Prepare', then '2. Plan', and so forth.
* | The template includes the following icons that represent:
The purpose of the specific section of the template providing the context or reason for the template.
An explanation of the required information to be added in the specific field.
SUCCESSFUL APPLICATION OF TECHNOLOGY CENTRED AROUND PEOPLE (SATCAP)
presents

## 1. Prepare
1. PREPARE
Steps in the "Prepare" phase
1.1 | Establish Project Team (Triangle2)
1.2 | Description, Case for Change & Impact Grading
1.3 | Stakeholder Impact Analysis
1.4 | Readiness Assessments
1.5 | Probability of Success Index
1.1 Establish Project Team (Triangle2)
Purpose: To provide structure for the digitisation strategy. It accounts for variables within a typical modernisation project. What makes this approach different is combining the strategic, project and operational levels within the Project Team with the Reinforcement Manager 'walking the talk' by leading from the front.
Establish Project Team (Triangle2)
Who will be the Change Leaders driving the implementation process of this project?
Click on each block for more information
#: | Change Leader: |  | Position Title: |  | Reason for Involvement: |  |  |  |  | Key Blueprint Tools: |  |  | Key Deliverables Expected: | [6 empty] | Readiness Level of Project Team:
i | Project Sponsor
[5 empty] | To gain commitment from senior leaders, dealing with any resistance/adoption on senior levels, and contextualise the modernisation journey for all other role-players. |  |  |  |  | 1.1 Establishing Project Team; 2.2 Technology Road Map & MOC; 2.3 Sponsor Plan
ii | Project Manager
[5 empty] | To deal with the overall project plan, timelines, and budget (resourcing) to deliver on the project's objectives on-time and within budget. |  |  |  |  | 1.5 Probability of Success Index; 2.1 Project Implementation Plan; 2.7 Enablement & Support Plan; 3.1 Run Pilot, Continoulsy Measure, Document Lessons Learnt & Adjust Plans; 4.1 Roll-Out Project, Continuously Measure, Document Lessons Learnt & Adjust Plans; 5.1 Hand-Over Enablement & Support Plan & 5.2 Mesure & Report Impact of Change Project
iii | Change Manager(s)
[5 empty] | To deal with the people side of change. To identify stakeholders, proactively mitigate resistance to the change, and facilitate the increase in adoption rates. |  |  |  |  | 1.3 Stakeholder Impact Analysis; 1.4 Readiness Assessments; 2.4 Stakeholder Engagement & Communication Plan; 2.5 Training & Coaching Plan; 2.6 Resistance to Change Plan
iv | Reinforcement Manager (s)
[5 empty] | As an employee-facing role, this manager must reinforce the plan through what is said, what is done and what the consequences are (positive or negative). |  |  |  |  | 2.4 Stakeholder Engagement & Communication Plan; 2.6 Resistance to Change Plan; 2.7 Enablement & Support Plan
v | IT Support / Technology Enablement Partner or Provider
[5 empty] | Remove obstacles and reduce risks to make it possible for the adopters through servicing the digitisation journey. |  |  |  |  | 1.2 Description, Case for Change & Impact Grading; 2.1 Project Implementation Plan
vi | Subject Matter Experts
[5 empty] | To provide clarity of the intent of the process and how this will be integrated into the organisational management systems. |  |  |  |  | 1.2 Description, Case for Change & Impact Grading
1.2 Description, Case for Change & Impact Grading
Purpose: To create a shared understanding and alignment between all stakeholders. It is a hymn sheet that assists in creating organisational alignment.
Description, Case for Change & Impact Grading
What will change?
Where will the change be implemented?
When will the change be implemented or need to be implemented?
What is the current state, or what problem will this change try to solve within the organisation?
Add Co-created or Affirmed Current Process: ('Day-in-the-Life-Off' Flow Chart)
What must the future state be or what opportunties will this change aim to develop?
Add Future Process: ('Day-in'the-Life-Off' Flow Chart)
What will the implications be if this change is NOT implemented?
What is required to make the change a success? (Critical Succes Factors)
What are existing limitations or could prevent the success of the change?
What are the intended benefits expected from implementing this change?
How will this technology benefit people?
How will the people be impacted? (TOP-Line)
|  |  | How will this change impact… | [10 empty] | No Impact | Very Low | Low | Medium | High | Very High | Positive or Negative Impact
Technologically | Tools |  | The tools/equipment people use to do their work? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| Maintenance/User Responsibility |  | The user's responsibilities regarding the tools/equipment and/or how it should be maintained? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| Modernisation Mindset |  | The user's mindset regarding modernisation? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
Organisationally | Processes |  | The process & procedures (way of work)? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| Reporting Methods |  | The way reporting is done? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| Support |  | The way support is provided within the organisation? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| Reporting Lines |  | Who the users report too? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
Personally | Skills |  | The users' knowledge, skills and/or experience? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| Position/Grading |  | The users' position or grading (money)? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| Workload |  | The users' workload? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| Hours/Working Schedule |  | The users' daily hours or working schedule? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
| New Behaviours |  | The way users should behave or will new behaviours be required? | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5
How will the organisation be impacted? (BOTTOM-Line)
|  |  | How will this change impact… (State the organisational aspects to be impacted) | [10 empty] | No Impact | Very Low | Low | Medium | High | Very High | Positive or Negative Impact
People (Learning & Growth) | [13 empty] | 0 | 1 | 2 | 3 | 4 | 5
Internal Business Processes | [13 empty] | 0 | 1 | 2 | 3 | 4 | 5
Stakeholder (Customer) | [13 empty] | 0 | 1 | 2 | 3 | 4 | 5
Financial | [13 empty] | 0 | 1 | 2 | 3 | 4 | 5
1.3 Stakeholder Impact Analysis
Purpose: To proactively identify the people impacted by this change, their respective influence on the project's success, and the degree of impact on their work life.
Stakeholder Impact Analysis
Who are the stakeholders that will be directly involved and/or affected by this change? (Rate the impact this change will have on each stakeholder and the importance of each stakeholder in terms of their influence over the success of the project?
Stakeholder: |  |  | Influence of Stakeholder over the Success of the Project: | [8 empty] | Impact of the Change on the Stakeholder:
|  |  | None | Very Low |  | Low |  | Medium |  | High | Very High | None | Very Low |  | Low |  | Medium |  | High |  | Very High
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
|  |  | 0 | 1 |  | 2 |  | 3 |  | 4 | 5 | 0 | 1 |  | 2 |  | 3 |  | 4 |  | 5
1.4 Readiness Assessments
Readiness Assessments
How ready is the organisation for this change?
1.4.1 Leaders' Readiness Assessment
Purpose: To measure the leaders' readiness to implement and adopt this technology to influence the preparations and planning process.
Leaders' Perception of the Readiness Assessment: (Complete this Readiness Assessment with each of the Leaders)
Individual Leader's Readiness: |  |  |  |  | Not Ready |  |  |  | Ready | Comments:
Can you describe the change initiative and the benefit for the Top & Bottom-line? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Can you demonstrate your own utilisation and proficiency regading this change? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Can you demonstrate how you will reinforce and support this change? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Technology & Systems' Readiness Assessment: |  |  |  |  | Not Ready |  |  |  | Ready | Comments:
Can you describe the requirements of the technology? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Can you demonstrate the functionality? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Can you demonstrate the sustainability and structure of support for the change? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Process, Policy & Procedure's Readiness Assessment: |  |  |  |  | Not Ready |  |  |  | Ready | Comments:
Can you describe the PPP related to this change? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Can you demonstrate the updated PPP for this change? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Can you demonstrate how the PPP will be reinforced and supported? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Risk & SHE Readiness Assessment: |  |  |  |  | Not Ready |  |  |  | Ready | Comments:
Can you describe the risk & SHE impact from this change? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Can you demonstrate the risk matrix for this change? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Can you demonstrate your risk mittigation process? |  |  |  |  | 1 | 2 | 3 | 4 | 5
1.4.2 Stakeholders' Readiness Assessment
Purpose: To measure the readiness of all other stakeholders regarding this technology and provide specific stakeholder-related resistance areas for focused change management interventions.
Stakeholders' Readiness Assessment: (Complete this Readiness Assessments with each Stakeholder)
Questions to Assess Change Readiness |  |  |  |  | Not Ready |  |  |  | Ready | Comments:
AWARENESS
Is there a problem with the current state/process? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Do you have any ideas on how to improve this? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Are you aware of any current developments/improvements underway? |  |  |  |  | 1 | 2 | 3 | 4 | 5
DESIRE
How important is it for you to change this? |  |  |  |  | 1 | 2 | 3 | 4 | 5
Do you see any benefits in changing this? |  |  |  |  | 1 | 2 | 3 | 4 | 5
KNOWLEDGE (Know how)
What is your level of knowledge to apply new technologies? |  |  |  |  | 1 | 2 | 3 | 4 | 5
ABILITY (Can do)
What will enhance your abilities to adopt new technologies? |  |  |  |  | 1 | 2 | 3 | 4 | 5
REINFORCEMENT
How do you see the current support for the adoption of new technologies? (Do they express, model and/or reinforce the change?) |  |  |  |  | 1 | 2 | 3 | 4 | 5
1.5 Probability of Success Index
Purpose: To provide an index that indicates the probability of success for the project. To show if an enabling environment exists for the implementation and adoption of the technology.
Probability of Success Index
Does this change project have a high probability of success? (Please complete the checklist to determine if you are ready to proceed to the Planning Phase)
[14 empty] | Not Yet |  | Partially |  | YES
1. | Have you established a Project Team with identified roles and deliverables ready to drive this change?
2. | Have you fully described the change with a detailed Case for Change, clearly showing the benefits to the people and the organisation?
3. | Have you identified all relevant stakeholders that will be affected by this change?
4. | Have you completed the Leaders' Readiness Assessments and it clearly showed that the organisation and it's leaders are ready to initiate this change?
5. | Have you completed the Stakeholder Readiness Assessments for all relevant stakeholders?
This Change Project's Current Probability of Success is:
Note on D20: State the NAME & SURNAME of each change leader as per their role in the Project Team.
Note on F20: State each change leader's Position Title as per the organisational structure.
Note on H20: State the reason this person was selected as a member of the Project Team.
Note on M20: State which templates the specific change leader should complete or contribute towards as part of the Project Team.
Note on S20: State the key deliverables / outcomes expected from this change leader for this project.
Note on Z20: Complete the Stakeholder Readiness Assessment on each change leader and then state each person's Readiness Level. NOTE: The whole Project Team must be at least on a level 4 to 5 before the process can start.
Note on F48: Describe the change you want to implement in one sentence.
Note on F49: State the scope of the implementation.
Note on F50: Describe the timeframe of the change implementation.
Note on F51: Describe the current way of doing things or state the problems this change is trying to solve.
Note on C52: Map or affirm the current co-created process indicating the process flow before implementing the new technology.
Note on F53: Describe how you want things to be done in the future or what the opportunities will be by implementing this change.
Note on C54: Map the future process indicating the process flow after implementing the new technology.
Note on F55: Describe the negative outcomes should the change not be implemented, delayed, or not successfully implemented.
Note on F56: Describe the factors required to make a success of implementing this change.
Note on F57: Describe the factors that could limit the success or completely derail the successful implementation of this change.
Note on F58: List the expected benefits of implementing this new technology for the organisation. Ensure that the expected benefits/value include expected cost benefits, level of the anticipated use of new technology, and the predicted quality level (i.e. Are people using the technology correctly?).
Note on F59: List specific benefits for the people that will be affected by the implementation of this new technology.
Note on C62: Rate how this new technology will impact people in terms of the list of criteria indicated.
Note on C77: Indicate the organisational aspects that will be impacted and then rate how this new technology will impact these aspects. Feel free to change the Performance Indicators to more relevant aspects depending on the specific project or your organisation.
Note on C90: Start by identifying and listing all the stakeholders involved or affected by this change. Then, rate each stakeholder's influence on the project's success (how influential they are in making the change work or not). Lastly, rate the impact that this change will have on each stakeholder. OUTCOME from ASSESSMENT: Prioritise stakeholders with medium to very strong influence as well as stakeholders that will be impacted (medium to very high).
Note on C113: Identify all the leaders within the organisation or the area where the change will be implemented. Then, assess their perception of the readiness for this change by asking each person to complete this Readiness Assessment. OUTCOME from ASSESSMENT: 1. To assess the readiness level of the leaders to reinforce and support the change; and 2. To assess the organisation's readiness level for implementing this change regarding its current technologies/systems, policies/processes/procedures, and potential risks/SHE impact.
Note on C140: Identify either all the stakeholders or a representative sample group of each stakeholder group. Then, assess their readiness for this change by asking each person to complete this Readiness Assessment. OUTCOME from ASSESSMENT: To assess the current readiness level of the stakeholder group. This information is then used as input in the planning phase to identify actions/interventions for each stakeholder group.
Note on C162: A quick 'Probability of success' test to determine if you are ready to proceed to the next phase in the change management process. The higher your score, the more likely you are to achieve success. If the score is low, we suggest you focus on gathering more information and completing some outstanding areas before continuing with the change management process.
Note on T169: After ticking the different boxes, add up your Probability of Success as follows: * For every 'Not Yet' answer, add 0% * For every 'Partially' answer, add 10% * For every 'YES' answer, add 20% The TOTAL from all five questions will indicate your project's current Probability of Success. Do not continue to the next phase until you have a high Probability of Success (At least 80%).

## 2. Plan
2. PLAN
Steps in the "Plan" phase
2.1 | Project Implementation Plan
2.2 | Technology Road Map & Management of Change (MOC)
2.3 | Sponsor plan
2.4 | Stakeholder Engagement & Communication Plan
2.5 | Training & Coaching Plan
2.6 | Resistance to Change Plan
2.7 | Enablement & Support Plan
2.1 Project Implementation Plan
Purpose: To provide an overall integrated view of the implementation and adoption process - a roadmap for the entire process.
Project Implementation Plan
How are you planning to implement this change and manage the identified risks?
Seq. | Action/Task Step | [6 empty] | Responsible Person | Schedule | Budget
TOTAL BUDGET =
2.2 Technology Road Map & Management of Change (MOC)
Purpose: To show how this project fits into the organisational digitisation journey and/or technology road map. To bring all the processes together, highlight the people-centredness of the planned implementation and adoption process.
Technology Road Map & Management of Change (MOC)
To be supplied, illustrated or submitted…
2.3 Sponsor plan
Purpose: To emphasise the commitment from the Sponsor to the project and all the stakeholders. To create an enabling environment for the success of the project.
Sponsor Plan
What are the activities of the Sponsor for each of the stakeholder groups?
Stakeholder Group: |  |  | Activities by Sponsor to Express, Model & Reinforce: |  |  |  |  | Schedule: (Date) | Comments:
Project Team
Operational Managers
Employees
2.4 Stakeholder Engagement & Communication Plan
Purpose: To provide a structured approach for the engagement with all the various stakeholders to increase their acceptance rate.
Stakeholder Engagement & Communication Plan
How are you planning to engage with and communicate to stakeholder groups?
Stakeholder: |  | Current Understanding & Needs/Concerns: |  | Communication Objective: |  | Discussion Approach & Key Message: |  | Messenger (Change Leader): | Method of Communication: | Communication Date:
2.5 Training & Coaching Plan
Purpose: To provide structure for identifying knowledge and skill deficiencies and the actions to close the identified gaps.
Training & Coaching Plan
How are you planning to provide the necessary training & coaching?
Description of Training |  | Audience | Intended Outcome |  | Method of Delivery |  | Tools & Equipment | Training Leader | Duration of Training | Cost of Training
2.6 Resistance to Change Plan
Purpose: To keep the correct people accountable by identifying possible reasons for resistance and the actions to address them.
Resistance to Change Plan
How are you planning to deal with resistance to change?
Stakeholder Resisting Change |  |  | Current ADKAR State: | Description of Resistance |  |  |  | Action to Address Resistance |  |  | Responsible Person | Scheduled Date
2.7 Enablement & Support Plan
Purpose: To proactively plan how this technology and the users will be supported after implementation. An operational handover by the Project Team.
2.7 Enablement & Support Plan
How are you planning to hand over the change to operations and further enable and support the change after implementation?
Seq. | Action/Task Step | [6 empty] | Responsible Person | Schedule | Budget
TOTAL BUDGET =
Note on B18: Develop an overall Project Plan for the implementation and adoption process. This template indicates the minimum requirements for all the necessary Action/Task Steps for the project in sequence, linked to a responsible person, with a milestone date for completion of the step and the required budget. NOTE: Feel free to use other templates, methodologies (Visual Mapping) or software (MS Projects) to create the Project Plan.
Note on B41: Add in or attach all supporting documents that provide an overview of the organisation's Technology Road Map for this change project and the Management of Change documentation (if necessary for this change).
Note on B50: State the activities to be completed by the Sponsor to express, model, and reinforce the change for each of the three identified stakeholder levels. How will the Sponsor champion and drive the overall message and project?
Note on B71: Informed by the stakeholder analysis and readiness assessments from Phase 1, create a plan for engaging and communicating with each stakeholder group.
Note on B90: Informed by the Stakeholder Readiness Assessments from Phase 1, create a plan to address any training/coaching needs for the various stakeholder groups.
Note on B107: Informed by the Stakeholder Readiness Assessments from Phase 1, create a plan to address the resistance to the change for each of the applicable stakeholder groups.
Note on B126: Develop a plan for handing over the implemented change to the operation showing how the change must be further enabled and supported continuously.

## 3. Pilot
3. PILOT
Steps in the "Pilot" phase
3.1 | Run Pilot, Continuously Measure, Document Lessons Learnt & Adjust Plans
3.1 Run Pilot, Continuously Measure, Document Lessons Learnt & Adjust Plans
Purpose: To test the systemic alignment of the technology in the real world. People, Process & Technology. To assess the user experience of the adoptors (co-creation and fine-tuning the roll-out plans).
Implement the pilot as per the Project Implementation Plan, Stakeholder Engagement & Communication Plan, Training & Coaching Plan, and the Resistance to Change Plan.
Document the lessons learnt:
|  | What worked well? | What did not work?
Are there any changes that need to be made to any of the plans going forward?
Note on B12: Document the lessons learnt during the Roll-Out Process. What worked and what didn't? Use this information to update all the Enablement & Support Plan.

## 4. Roll-Out
4. ROLL-OUT
Steps in the "Roll-Out" phase
4.1 | Roll-Out Project, Continuously Measure, Document Lessons Learnt & Adjust Plans
4.1 Roll-Out Project, Continuously Measure, Document Lessons Learnt & Adjust Plans
Purpose: To roll out the technology throughout the organisation, institutionalise the people processes and prepare for the operational handover.
Implement the Roll-Out as per the Project Implementation Plan, Stakeholder Engagement & Communication Plan, Training & Coaching Plan, and the Resistance to Change Plan.
Document the lessons learnt:
|  | What worked well? | What did not work?
Are there any changes that need to be made to the Enablement & Support Plan?
Note on B12: Document the lessons learnt during the Roll-Out Process. What worked and what didn't? Use this information to update all the Enablement & Support Plan.

## 5. Support
5. SUPPORT
Steps in the "Support" phase
5.1 | Implement Enablement & Support Plan, Hand-Over to Operations and Continuously Support, Measure & Adjust
5.2 | Measure & Report on the Impact of the Change Project
5.1 Implement Enablement & Support Plan, Hand-Over to Operations and Continuously Support, Measure & Adjust
Purpose: To hand-over the implemented technology after the roll-out phase to accountable persons for the on-going support.
Hand-Over Plan:
Who are you handing over to? |  |  | When are you planning to hand over? | Why are you handing over to this person? | What will be expected from this person?
Are there changes that should be made to the Enablement & Support Plan after the Hand-Over?
5.2 Measure & Report Impact of the Change Project
Purpose: To state the successes and measurable outcomes achieved through the implementation of this change project. In addition, to document any lessons learnt that could benefit future change projects.
What are the successes of the project to date?
Did the project achieve the desired outcomes/benefits/expected value?
Indicator: |  | Expected Outcome: | Actual Outcome: | Achieved or Not? | Comment:
Time
Cost
Utilisation
Quality
Other
Are there any lessons learnt for future projects?
Congratulations on completing the Change Management Blueprint Templates! Take the lessons learnt from this project as input into your next change initiative as part of the continuous improvement process.
Note on B12: After implementation, the ongoing support must be handed over to operations. Who are you planning to hand over this responsibility to? When will they take over this responsibility? Why is this person best suited to take over this responsibility? What will be expected from them going forward?
Note on B20: The Hand-Over should be a face-to-face meeting where the Enablement & Support Plan is discussed. Note any changes that must be made to the plan going forward after discussions with the accountable individuals.
Note on B32: Describe the successes achieved through the implementation and adoption process of the specific change.
Note on B38: Provide measurable results achieved through the project using the following structure: Time - What was the original planned project timeline vs. the actual time when the project was handed over to operations? Cost - What was the original planned budget/cost saving for this project vs. the actual budget/cost saving in the end? Utilisation - What was the original planned level of utilisation from the target audience expected vs. now during hand-over? Quality - What was the expected quality (are people using it correctly) vs. now during the handover? Feel free to change or customise the indicators per your project's requirements.
Note on B47: List any lessons learnt that could benefit future projects. These will be used as input into future change management projects.